## Product Backlog
Product Name: | JADE Manager | [5 empty] | Complete Fields in Green!!!
Team ID: | 1001819680
| Team Member Name |  |  |  |  | Initials | Student ID
Required | Chau-Phuc Nguyen |  |  |  |  | C.N | 1001819680
Sprint # | Remaining | Completed This Sprint |  |  | Comment
0 | 35 |  |  | Total | Total number of features (in column H)
1 | 32 | 3 |  | 1 | Total features left at the end of Sprint #1
2 | 29 | 3 |  | 2 | Total features left at the end of Sprint #2
3 | 29 | 0 |  | 3 | ...and so on
4 | 29 | 0
5 | 28 | 1
6 | 28 | 0
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
|  |  |  | Sprints |  | Features are always graded at the end of the sprint in which they are required, regardless of when they are implemented
Feature ID | Priority | Required | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 | 13 | 1 | Finished in Sprint 1 | Manager | Create a new coffee flavor | Stock and sell coffee products
CC | 2 | 1 | 5 | 1 | Finished in Sprint 1 | Manager | Create a new donut | Stock and sell donuts
STOR | 3 | 1 | 13 | 1 | Finished in Sprint 1 | Manager | Manage a list of coffee and donut products per store | Manage training and advertising
GUI | 4 | 2 | 8 | 2 | Finished in Sprint 2 | Manager | Use a main window (GUI) with simple menu bar tool bar | Reduce training costs | This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
IGUI | 5 | 2 | 21 | 2 | Finished in Sprint 2 | Manager | Use dialogs to create new coffee and donut products | Reduce training costs | Sequence of dialogs OK for initial prototype. One dialog each for coffee and for donuts is below.
CE | 6 | 3 | 13 | 2 | Finished in Sprint 2 | Manager | Create a new store | Franchise JADE operations | This includes all data in a store, including new features implemented in later sprints
SAVD | 7 | 3 | 8 | 3 | In Work | Manager | Save all data to a default file on exit or command | Ensure our data isn’t lost | This includes all data in a store, including new features implemented in later sprints
LOAD | 8 | 3 | 5 | 3 | In Work | Manager | Load data from a default file on startup | Ensure our data isn’t lost | This includes all data in a store, including new features implemented in later sprints
SALL | 9 | 3 | 5 | 3 | In Work | Owner | Save all data to a specified file | Franchise my company | Use the File Chooser dialog (see Lecture 15)
LALL | 10 | 3 | 5 | 3 | In Work | Owner | Load data from a specified file | Franchise my company | Use the File Chooser dialog (see Lecture 15)
PS | 11 | 4 | 5 |  | In Test | Customer | List all coffee and donut products in a dialog | See what is available (and later, see what the Customer can order) | This is effectively a toString to a dialog with an OK button
CB | 12 | 4 | 2 |  | In Test | Server | Create a new beloved customer | Keep track of our customers
CO | 13 | 4 | 8 |  | In Test | Server | Create an order of multiple products | Serve everyone in a customer party
POC | 14 | 4 | 3 |  | In Work | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB | 15 | 4 | 8 |  | In Work | Customer | Associate the order with a customer | Self-order and not have to deal with people | “What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
CS | 16 | 5 | 5 |  | Finished in Sprint 5 | Server | Create a new named server and associate with orders | Track server productivity and tips
CM | 17 | 5 | 3 |  | In Work | Owner | Create a new manager | Delegate management tasks to a pro
P&L | 18 | 5 | 8 |  |  | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy | Demonstrate the use of Java iterators with this feature
RTM | 19 | 5 | 8 |  |  | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members | Demonstrate the use of Java iterators with this feature
UD | 20 | 6 | 21 |  |  | Manager | Create unified dialogs across the application | Interact more efficiently with the program | Each command (e.g., Create > Donut) should required a single dialog
EF | 21 | 6 | 8 |  |  | Manager | Edit a product | Improve our data and keep it synced to reality
The Features below are BONUS work. If implemented, they will be graded, and the bonus awarded, at the end of Sprint 6
|  | Bonus |  |  |  | (If a Bonus feature changes AFTER you have implemented it, please notify the Professor ASAP)
PIX | 22 |  | 21 |  |  | Customer | Add and display pictures for each item | Better understand the menu | Pics would be added on product creation, and displayed when composing a new order
ASTO | 23 |  | 8 |  |  | Manager | Also associate a server with the order they fill | Keep track of our employee productivity
XT | 24 |  | 13 |  |  | Manager | Suspend a server (no longer allow their selection for an order, but keep their historical data) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 25 |  | 5 |  |  | Manager | Restore a server | Add a former team member tack into service
TIPS | 26 |  | 8 |  |  | Server | Calculate a percentage of each order served and report on each Server’s tips | Pay tip income as well as salary to Servers
AI | 27 |  | 8 |  |  | Server | Restock donuts and coffees | Ensure we can fill every order
MST | 28 |  | 5 |  |  | Manager | Manage the state of each order (unfilled -> filled and unpaid -> paid,, or unfilled / unpaid -> canceled) | Ensure each order is filled and payment collected | This is a good bonus problem if you attend the (optional) Lecture 24 on state machines
POS | 29 |  | 5 |  |  | Server | Show the products in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
RI | 30 |  | 5 |  |  | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
RO | 31 |  | 8 |  |  | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 32 |  | 5 |  |  | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
ROA | 33 |  | 3 |  |  | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
CENEW | 34 |  | 13 |  |  | Owner | Create a new franchise | Franchise my company
XI | 35 |  | 21 |  |  | Manager | Retire a product (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-10-05 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-10-12
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 0 | 3
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CF | C.N | finished java | Completed Day 1
2 | CC | C.N | finished donut | Completed Day 1
3 | STOR | C.N | finished store | Completed Day 1
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-10-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-10-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 3
Day 1 Left | 3 | 0
Day 2 Left | 2 | 1
Day 3 Left | 2 | 0
Day 4 Left | 2 | 0
Day 5 Left | 2 | 0
Day 6 Left | 2 | 0
Day 7 Left | 2 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | GUI | C.N | debugging GUI | In Work
2 | IGUI | C.N | DEBUGGING IGUI | In Work
3 | CE | C.N | FINISHED CE | Completed Day 2
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-10-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-10-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 4 | 0
Day 7 Left | 4 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SAVD | C.N | CURRENTLY TESTING | In Work
2 | LOAD | C.N | CURRENTLY TESTING | In Work
3 | SALL | C.N | CURRENTLY TESTING | In Work
4 | LALL | C.N | CURRENTLY TESTING | In Work
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-11-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-11-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 5
Day 1 Left | 5 | 0
Day 2 Left | 5 | 0
Day 3 Left | 5 | 0
Day 4 Left | 5 | 0
Day 5 Left | 5 | 0
Day 6 Left | 5 | 0
Day 7 Left | 5 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | PS | C.N | CURRENTLY TESTING | In Work
2 | CB | C.N | CURRENTLY TESTING | In Work
3 | CO | C.N | CURRENTLY TESTING | In Work
4 | POC | C.N | CURRENTLY IN WORK | In Work
5 | CSB | C.N | CURRENTLY IN WORK | In Work
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-11-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-11-16
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 2
Day 1 Left | 2 | 0
Day 2 Left | 2 | 0
Day 3 Left | 2 | 0
Day 4 Left | 2 | 0
Day 5 Left | 2 | 0
Day 6 Left | 1 | 1
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CS | C.N | FINISHED CS | Completed Day 6
2 | CM | C.N | CURRENTLY IN WORK | In Work
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-11-30 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-12-07 |  | NOTE: A stand-alone assignment on threading is Nov 16-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84